## Sheet1
Sprint Backlog - 4
Sl. No. | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a shop owner, have different accounts and have access to create new accounts so that, I can get privilege to my manager(s) and me | Design the user database | 1 hour | 0 | 0 | 0 | 0 | 0 | 0
|  | Design the user interface | 0 | 3 hours | 0 | 0 | 0 | 0 | 0
|  | Code the class | 0 | 0 | 2 hours | 3 hours | 0 | 0 | 0
|  | Test the class | 0 | 0 | 0 | 1 hour | 0 | 0 | 0
|  | Test the system | 0 | 0 | 0 | 0 | 1 hour | 1 hour | 0
2 | As shop owner, have access of all the items in a software and the managers should have a selected few items so that, I can get the overall view and the managers can use only the items selected by me | Code the necessary classes | 0 | 2 hours | 2 hours | 0 | 0 | 0 | 0
|  | Test the classes | 0 | 0 | 0 | 1 hour | 0 | 0 | 0
|  | Test the system | 0 | 0 | 0 | 0 | 1 hour | 1 hour | 0
3 | As a manager, Have a product refund and return system so that, when customer returns a product it can go back in the inventory | Code the necessary classes | 0 | 0 | 0 | 0 | 2 hours | 2 hours | 2 hours
|  | Test the classes | 0 | 0 | 0 | 0 | 0 | 1 hour | 0
|  | Test the system | 0 | 0 | 0 | 0 | 0 | 0 | 0