## Sheet1
Sprint Backlog - 1
Sl. No. | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a manager, I want to have acces to add new products in the inventory so that, when new products arrive I can easily add them in the inventory | Design the product database | 0 | 0 | 0 | 1 hour | 1 hour | 0 | 0
|  | Design the user interface | 0 | 0 | 0 | 0 | 1 | 1 hour | 0
|  | Code the classes | 0 | 0 | 0 | 0 | 0 | 1 hour | 1 hour
|  | Test the classes | 0 | 0 | 0 | 0 | 0 | 0 | 1 hour
|  | Test the system | 0 | 0 | 0 | 0 | 0 | 0 | 1 hour