## Sheet1
Product Backlog
Sl. No. | As a… | I want to… | So that… | Priority | Sprint | Status
1 | Manager | Have the access to add new products in the inventory | When new products arrive I can easily add them in the inventory | High | 1 | In Progress
2 | Shop Owner | My manager to not have the access to delete products | They can not hide products from the software | High | 2 | In Progress
3 | Shop Owner | Sell products using this software | I can sell products to my customers using it without any sort of error in calculation | High | 2 | Not Started
4 | Shop Owner | A sales report option | I can check and track all the sale details | High | 2 | Not Started
5 | Manager | Have records of all my products in the store | I can get to know how many products I have in store | High | 2 | Not Started
6 | Manager | Have a product refund and return system | When customer returns a product it can go back in the inventory | High | 3 | Not Started
7 | Shop Owner | Have different accounts and have access to create new accounts | I can get privilege to my manager(s) and me | Medium | 3 | Not Started
8 | Shop Owner | Have access of all the items in a software and the managers should have a selected few items | I can get the overall view and the managers can use only the items selected by me | Medium | 3 | Not Started
9 | Shop Owner | Have access to add new managers, update manager privileges and delete manager accounts | I can keep records of the managers information and invoke and revoke their privileges | Medium | 4 | Not Started
10 | Shop Owner | Have records of all my suppliers and the supply records | I can keep full records of every supply of all te suppliers | Medium | 4 | Not Started
11 | Manager | Have a cutomer database | I can manage a customer membership facility in order to keep track of special customers | Low | 4 | Not Started
12 | Shop Owner | Change my password and other informations | I can customize my profile and make my account more secure | Low | 4 | Not Started