## Sheet1
Sprint Backlog - 2
Sl. No. | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a shop owner, I don't want my manager to have access to delete products so that, they can not hide products from the software. | Design the user login system | 0 | 0 | 0 | 1 hour | 1 hour | 0 | 0
|  | Designing the user database | 0 | 0 | 0 | 0 | 1 | 1 hour | 0
|  | Code the class | 0 | 0 | 0 | 0 | 0 | 1 hour | 1 hour
|  | Test the class | 0 | 0 | 0 | 0 | 0 | 0 | 1 hour
|  | Test the system | 0 | 0 | 0 | 0 | 0 | 0 | 1 hour
2 | As a shop owner, I want to sell products using this software so that, I can sell products to my customers using it without any sort of error in calculation. | Design the product database | 1 hour | 1 hour | 0 | 0 | 0 | 0 | 0
|  | Design the user interface for sale management | 0 | 1 hour | 0 | 0 | 0 | 0 | 0
|  | Code the necessary classes | 0 | 0 | 3 hours | 2 hours | 0 | 0 | 0
|  | Test the classes | 0 | 0 | 0 | 0 | 2 hour | 0 | 0
|  | Test the system | 0 | 0 | 0 | 0 | 0 | 1 hour | 1 hour