## Sheet1
Sprint Backlog - 3
Sl. No. | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a shop owner, I want to have a sales report option so thar, I can check and track all the sale details | Design the sales database | 1 hour | 1 hour | 0 | 0 | 0 | 0 | 0
|  | Code the class | 0 | 0 | 3 hours | 3 hours | 2 hours | 0 | 0
|  | Test the class | 0 | 0 | 0 | 0 | 1 hour | 0 | 0
|  | Test the system | 0 | 0 | 0 | 0 | 0 | 1 hour | 1 hour
2 | As a manager, I want to have records of all my products in the store so that, I can get to know how many products I have in store | Connect the database with the appropriate class | 2 hours | 1 hour | 0 | 0 | 0 | 0 | 0
|  | Design the user interface for showing sale report | 0 | 2 hours | 0 | 0 | 0 | 0 | 0
|  | Code the necessary classes | 0 | 0 | 2 hours | 0 | 0 | 0 | 0
|  | Test the classes | 0 | 0 | 0 | 0 | 1 hour | 0 | 0
|  | Test the system | 0 | 0 | 0 | 0 | 1 hour | 1 hour | 0